## Input
Estimation
Testing Estimation Split
| Nos of Components based on Complexity |  |  |  | Total
Customization Type | Small | Simple | Medium | Complex | Components | Efforts (mandays)
Test Planning and Preparation | 1 | 1 | 1 | 1 | 4 | 6.5
User Registration Testing | 1 | 1 | 1 |  | 3 | 1.75
Office Place Booking Testing | 1 | 1 | 1 | 1 | 4 | 10
Mobile Application Testing | 1 | 1 |  | 1 | 3 | 4.5
Office Place Management Testing | 1 | 1 | 1 | 2 | 5 | 14
Integration and Regression Testing | 1 |  | 1 | 1 | 3 | 5.5
Usability and User Experience Testing | 1 | 1 | 1 |  | 3 | 6
Performance Testing |  |  |  |  | 0 | 0
Build Effort | 7 | 6 | 6 | 6 | 25 | 48.25
Weightage | 0.05 | 0.15 | 0.3 | 0.5 | 0.1
High-Level Description of Test Activities Summing Up in a Process:
The test activities are strategically planned to cover all aspects of the new features and their integration with the existing functionality. The process includes a comprehensive testing approach that encompasses functional testing, usability testing, performance testing, and compatibility testing across different devices and platforms. Test planning and preparation are crucial to ensure that the testing effort is well-organized and efficient.
The testing process involves close collaboration between the testing team, development team, and stakeholders. Regular communication and feedback loops facilitate quick identification and resolution of issues. The focus is on delivering a high-quality product that meets customer expectations, provides a user-friendly experience, and supports a seamless workflow for both users and office managers.

## Estimation
NHS SBS
BI Effort Estimation
CR Description |  | #REF! |  | Estimator - Build |  | #REF!
CR Number |  | #REF! |  | Estimator - Testing |  | #REF!
Environment |  | #REF! |  | Estimation Date |  | #REF!
Efforts (In mandays)
Environments |  |  |  |  | #REF!
Build Efforts |  |  | 48.25 |  | #REF!
Data Load Efforts |  |  |  |  | #REF!
Total Components |  |  |  |  | 25
Documentation |  |  |  |  | 0
|  | Technical Documents | 0 |  |  | Already completed in assessment stage
|  | Test Plan | 0
Unit Testing |  |  |  |  | #REF!
Review |  |  |  |  | #REF!
| Technical Document |  | 0 |  |  | Already completed in assessment stage
| Test Plan |  | 0
| Build |  | #REF!
UAT Code Deployment |  |  |  | 1.21 | #REF! | Code and Data Load
UAT Support |  |  |  |  | #REF!
Testing Team Effort |  |  |  |  | #REF!
Pre-testing |  | Preparation |  |  | #REF!
|  | Execution |  |  | #REF!
Post-testing |  | Preparation |  |  | #REF!
|  | Execution |  |  | #REF!
Test Closure |  | Test Completion Report |  |  | #REF!
Total Efforts |  |  |  |  | #REF! | Without Contigency
Contingency |  |  |  |  | #REF!
| Solution Designing is complete & Documented |  | Yes |  |  |  | 0.25
| Requirements Documented |  | Yes |  |  |  | 0.25
| Feasibility of Requirements Accepted |  | Yes |  |  |  | 0.25
| Complexity |  | Complex |  |  |  | 2.5
| Size |  | #REF! |  |  |  | #REF!
Total Efforts (including Contingency) |  |  | #REF!

## Efforts Guidelines
Component | Small | Simple | Medium | Complex
Database Objects(Table, Index, Column) - New | 0.5 | 1 | 2 | 3
Database Objects(Table, Index, Column) - Existing | 0.25 | 0.5 | 1 | 1.5
SQL Query - New | 1 | 2 | 3 | 4
SQL Query - Existing | 0.5 | 1 | 2 | 3
Informatica Mapping - New | 1 | 2 | 3 | 4
Informatica Mapping - Existing | 0.5 | 1 | 2 | 3
Informatica Scheduler - New | 1 | 2 | 3 | 4
Informatica Scheduler - Exisiting | 0.5 | 1 | 2 | 3
File Load Process - New | 1 | 1 | 2 | 3
File Load Process - Existing | 1 | 1 | 2 | 3
Historic Data Load - Current Financial Year | 0.5 | 1 | 3 | 5
Historic Data Load - Current Financial Year and Current -2 yrs | 1 | 2 | 5 | 8
Historic Data Load - Full Load | 2 | 3 | 7 | 12
DAC - New | 1 | 1 | 2 | 4
DAC - Exisiting | 0.5 | 1 | 1.5 | 2
RPD Subject Area - New | 0 | 2 | 4 | 6
RPD Subject Area - Existing | 0.5 | 1 | 2 | 4
Report - New | 0.5 | 1 | 2 | 4
Report - Existing | 0.25 | 0.5 | 1 | 2
Dashboard Page- New | 1 | 1 | 2 | 4
Dashboard Page- Existing | 0.5 | 1 | 2 | 3
Dashboard - New | 1 | 2 | 3 | 4
Dashboard - Existing | 0.5 | 1 | 2 | 4
Security - New | 1 | 2 | 3 | 4
Security - Existing | 0.5 | 1 | 2 | 3
Customization Type | Small | Simple | Medium | Complex
Pre - Fix Scenarios # Preparation |  | 0.1 | 0.1 | 0.25
Pre - Fix Scenarios # Execution |  | 0.1 | 0.15 | 0.25
Post - Fix Scenarios # Preparation |  | 0.1 | 0.1 | 0.25
Post - Fix Scenarios # Execution |  | 0.1 | 0.15 | 0.25
Test Completion Report |  | 0.25 | 0.3 | 0.5